## Slide 1
DATA STRATEGY TOOLKIT
Strategy Workshop Kit
Three leadership workshops that turn the business strategy into a data strategy and a scorecard
scikiq.org/data-strategy

## Slide 2
THE SO WHAT OF THIS DECK
Run the workshops in sequence to agree themes, the strategy map and the use-case portfolio, and leave every session with named owners and dates.
SCIKIQ | Strategy Workshop Kit
2

## Slide 3
The workshop series
Half a day each, two weeks apart, the same core group.
1
Workshop 1: Strategy to map
Confirm vision, choices and themes; build the strategy map; find where data enables it
2
Workshop 2: Data objectives and portfolio
Write data objectives, set the offence and defence posture, rank the portfolio
3
Workshop 3: Scorecard and commitments
Agree measures, targets, owners, gates, forums and the first 100 days
SO WHAT
Three half-days, two weeks apart, produce the map, the data objectives, the scorecard and the commitments.
SCIKIQ | Strategy Workshop Kit
3

## Slide 4
Who attends, and their role
Participant | Role in the room
Executive sponsor | Opens, frames the ambition, breaks ties
Theme owners | Own objectives and measures; commit people
Head of data | Brings the baseline and portfolio; owns the plan
Finance partner | Tests value, baselines and funding
Facilitator | Runs the process, keeps time, stays neutral
Note-taker | Captures decisions and actions live
SCIKIQ | Strategy Workshop Kit
4

## Slide 5
Workshop 1: strategy to map
Time | Session | Output
0:00 | Vision, mission and choices: playback and challenge | Confirmed cascade top
0:40 | Themes and owners | Three to five themes with owners
1:20 | Build the strategy map in four perspectives | Draft objectives
2:20 | Draw and test the cause-and-effect links | Linked map
3:00 | Mark objectives that depend on information | Data hot spots
3:30 | Decisions and homework | Decision log
SCIKIQ | Strategy Workshop Kit
5

## Slide 6
Workshop 2: data objectives and portfolio
Time | Session | Output
0:00 | Data hot spots to data objectives | Five to six data objectives with map IDs
0:50 | Posture: offence and defence | Agreed balance and why
1:30 | Use cases: value at stake and feasibility | Scored long list
2:30 | The cut line and the not-now list | Ranked portfolio
3:15 | Shared data products | Build-once list
3:40 | Decisions and homework | Decision log
SCIKIQ | Strategy Workshop Kit
6

## Slide 7
Workshop 3: scorecard and commitments
Time | Session | Output
0:00 | Measures for each objective: lead and lag | Draft scorecard
0:50 | Baselines, targets and owners | Committed targets
1:40 | Initiatives and stage gates | Funded first tranche
2:20 | Forums, decision rights and rhythm | Operating model
3:00 | First 100 days | Plan with owners
3:30 | Strategy on a page | Agreed one-pager
SCIKIQ | Strategy Workshop Kit
7

## Slide 8
Exercises that work
Test the arrows
For each link on the map ask: what evidence says this causes that? Weak links become review hypotheses.
Pre-mortem
Two years on, the strategy failed. Why? Turn the answers into risks and leading measures.
Posture vote
Each leader places a dot on the offence to defence line; debate the spread, not the average.
Value vs feasibility
Place each use case on the matrix; debate only where scores disagree.
Measure or opinion?
For every proposed measure: could someone else reproduce it next month?
Not-now list
Agree explicitly what the strategy will not do this cycle.
SCIKIQ | Strategy Workshop Kit
8

## Slide 9
Internal or external facilitator?
Choose internal when
The group works well together
Topics are not contentious
You have a skilled, neutral facilitator
Choose external when
Strong views or politics are in play
Past sessions did not reach decisions
You need everyone, including the data lead, to participate
SCIKIQ | Strategy Workshop Kit
9

## Slide 10
Decision log
Decision | Rationale | Owner | Due
[Decision] | [Why] | [Name] | [Date]
[Decision] | [Why] | [Name] | [Date]
[Decision] | [Why] | [Name] | [Date]
[Decision] | [Why] | [Name] | [Date]
[Decision] | [Why] | [Name] | [Date]
[Decision] | [Why] | [Name] | [Date]
SO WHAT
Publish the log within 24 hours; a decision not written down was not made.
SCIKIQ | Strategy Workshop Kit
10

## Slide 11
Follow-up and follow-through
Send the decision log within 24 hours
Confirm owners and dates individually
Show the first visible action within two weeks
Start the monthly scorecard review straight away
scikiq.org/data-strategy
SCIKIQ | Strategy Workshop Kit
11